FY13 PROJECT CHECKLIST

Each item must be completed during the FY13 grant year in a timely manner.

| CHECK | DUE DATE | ITEM |
| --- | --- | --- |
|  | Aug 2012 ASAP | All POs for FY11 spending due. NONE HONORED IN SEPTEMBER. |
|  | Aug 10, 2012 | Last day to count on time sheets |
|  | Aug 14, 2012 | Time sheets due by NOON in Central Office |
|  | Aug 2012 | Update student folders for summer participants. They count for the FY13 reports! |
|  | Aug 2012 | Check with counselors, administrators for recs on student participants |
|  | Aug 2012 | Advertise your program: Press release to J Caton, flyers/letters sent home |
|  | Aug 2012 | Newsletter covering summer, cc to me |
|  | Aug 2012 | Recruit potential staff members |
|  | Aug 2012 | Revise Handbook for Orientation if needed |
|  | Aug 2012 | Distribute materials at your school’s Open House |
|  | Aug 2012 | Print, distribute applications |
|  | Aug 2012 | Collect applications, select participants |
|  | Aug 2012 | Prepare “wait list” to use as soon as a participant drops out |
|  | Aug 2012 | Family Orientation night for new attendees |
|  | Aug 2012 | Collect signed agreements |
|  | Aug 2012 | Make sure you have receipt books |
|  | Aug 2012 | Begin your program |
|  | Aug or Sept | Sign PARTNER AGREEMENT contract with a collaborative community entity. CC to me. |
|  | Sept 14, 2012 | Last day to count on time sheets, BUT ESTIMATE HOURS THROUGH SEPT. 28. |
|  | Sept 17, 2012 | Time sheets due by NOON in Central Office |
|  | Early Sept 2012 | All invoices for FY12 spending due in the Accounting Office. CALL late vendors!! |
|  | Sept 2012 | Staff training/professional development. Share video information. |
|  | Sept 2012 | Send Family Activities packets home |
|  | Sept 2012 | Share Study Skills booklet with faculty |
|  | Oct 12, 2012 | Last day to count on time sheets. This will be a short month. |
|  | Oct 15, 2012 | Time sheets due by NOON in Central Office |
|  | Oct 2012 | Inspection/evaluation by Project Administrator and/or state consultant |
|  | Nov 2 | Last day to count on time sheets |
|  | Nov 5 | Time sheets due by NOON in Central Office |
|  | Nov 2012 | Inspection/evaluation by Project Administrator and/or state consultant |
|  | Dec 7,2012 | Last day to count on time sheets |
|  | Dec 10, 2012 | Time sheets due by NOON in Central Office |
|  | Dec 2012 | Inspection/evaluation by Project Administrator and/or state consultant |
|  | Jan 11, 2013 | Last day to count on time sheets |
|  | Jan 14, 2013 | Time sheets due by NOON in Central Office |
|  | Feb 2013 | Inspection/evaluation by Project Administrator and/or state consultant |
|  | Feb 8, 2013 | Last day to count on time sheets |
|  | Feb 11, 2013 | Time sheets due by NOON in Central Office |
|  | Mar 8, 2013 | Last day to count on time sheets |
|  | Mar 11, 2013 | Time sheets due by NOON in Central Office |
|  | March 2013 | Advertise summer program |
|  | March 2013 | All SUMMER field trip planning sheets, contracts, documentation, POs |
|  | March or April | Register SUMMER participants. Take up deposit or full tuition. DEPOSIT IT! |
|  | April 12, 2013 | Last day to count on time sheets |
|  | April 15, 2013 | Time sheets due by NOON in Central Office |
|  | April 2013 | Inspection/evaluation by Project Administrator and/or state consultant |
|  | April 2013 | Student, teacher and parent surveys. Tally and keep them for APR report. |
|  | May 10, 2013 | Last day to count on time sheets |
|  | May 13, 2013 | Time sheets due by NOON in Central Office |
|  | May 2013 | All date for APR and DEAR turned in to me BEFORE THE LAST DAY OF SCHOOL! |
|  | May 2013 | Family Orientation for summer program. ALL TUITION DUE. DEPOSIT IT! |
|  | May 2013 | End FY13 data collection. FY 14 data begins with new SUMMER student folders. |
|  | May 2013 | Inspection/evaluation by Project Administrator and/or state consultant |
|  | May 2013 | Award program / Family Night |
|  | Spring 2013 | Work with admin for new grant application, new budget |
|  | June, first two weeks | SUMMER PROGRAM. Make up weeks “owed” to school last two weeks. |
|  | June 14, 2013 | Last day to count on time sheets. Summer program should be over. |
|  | June 17, 2013 | Time sheets due by NOON in Central Office |
|  | June 2013 | 80 hours of programming, 4 days for 2 weeks, 8 field trips. |
|  | June 2013 | Have all emergency numbers, contact numbers etc with you on field trips |
|  | July ASAP | If you run Summer after June 14, get time sheets in as soon as you are finished. |
|  | July ASAP | Email me when they are in my mailbox. Only teachers and aides will be paid. |
|  | July 2013 | No pay for 21CCLC Site Directors |
|  | Aug 2013 | All POs for FY13 spending due. NONE HONORED IN SEPTEMBER. |
|  | Sept 6, 2013 | All invoices for FY13 spending due. CALL late vendors!! |
|  | Daily | Keep attendance records |
|  | Daily | Snack from CNP |
|  | Daily | Physical exercise |
|  | Daily | Academic reinforcement: language arts, mathematics, social studies |
|  | Daily | Reinforcement/remediation of classroom lessons |
|  | Daily | Enrichment activities |
|  | Weekly | Natural sciences, computer skills, fine arts, character ed and/or service learning |
|  | Weekly | Collect and deposit tuition. Receipt tuition payments. DEPOSIT IT! |
|  | Weekly | Send “tuition due” notices to anyone failing to pay. After 2 weeks, drop them. |
|  | Weekly | Prepare lesson plans, staff schedules, enrichment, academics |
|  | Monthly | Reconcile your budget with report from Central Office |
|  | Monthly | Fax/send lesson plans and attendance report to CNP |
|  | Monthly | Turn in time sheets and monthly report |
|  | As needed | Create folder for each child for ARMT scores, office referrals, documents |
|  | As needed | Replenish supply of “IT’S APPARENT” brochures in your lobby rack |
|  | As needed | Document each personal contact with parent and/or child |
|  | As needed | Keep up with all subcontractors, volunteers and partners during the FY13 year |
|  | As needed | Keep up with and properly mark/store all inventory |
|  | As needed | Supervise staff, provide feedback, make assignments |
|  | As needed | Update 21CCLC website or your info on school website |
|  | On all drill days | Document same safety drills for the afternoon |
|  | 1st Semester | At least one Family Night, program with parenting skills |
|  | 1st Semester | Advisory Council meeting, invitation/announcement, agenda, sign in sheet |
|  | 1st Semester | At least 4 hours professional development for all involved (can be provided by system) |
|  | 1st Semester | Service project to help the community (may or may not be service learning) |
|  | 1st Semester | Service learning project |
|  | 1st Semester | Collaboration with community group/organization |
|  | 2nd Semester | At least one Family Night program with parenting skills |
|  | 2nd Semester | Advisory Council meeting, invitation/announcement, agenda, sign in sheet |
|  | 2nd Semester | At least 4 hours professional development for all involved (can be provided by system) |
|  | 2nd Semester | Service project to help the school (may or may not be service learning) |
|  | 2nd Semester | Collaboration with community group/organization |